## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project (Chat with Documents) | MUST HAVE | No Dependency | Aditya Chikte | 3- Completed
S1 | S1 | US-002 | Workflow Creation and Project Goal Documentation | MUST HAVE | Lucid Chart | Aditya Chikte | 3- Completed
S1 | S1 | US-003 | Research: Understanding Chatbot Architecture and Document Processing | MUST HAVE | Online Articles, Research Papers | Aditya Chikte | 3- Completed
S2 | S2 | US-004 | Document Parsing Techniques: Research on PDF and DOCX Parsing Approaches | MUST HAVE | Python Libraries (PyPDF2, docx) | Aditya Chikte | 3- Completed
S2 | S2 | US-005 | Use Case Identification and Initial Preparation | SHOULD HAVE | No Dependency | Aditya Chikte | 3- Completed
S3 | S3 | US-006 | Python Programming Kit Practice Completion | MUST HAVE | HackerRank, W3Schools | Aditya Chikte | 3- Completed
S3 | S3 | US-007 | Flask Backend Setup and API Integration | MUST HAVE | Flask Framework | Aditya Chikte | 3- Completed
S4 | S4 | US-008 | SQL Programming Kit Practice Completion | MUST HAVE | HackerRank, W3Schools | Aditya Chikte | 3- Completed
S4 | S4 | US-009 | Frontend Development: Creating Basic UI with Next.js and Tailwind CSS | MUST HAVE | Tailwind CSS, Next.js Documentation | Aditya Chikte | 3- Completed
S5 | S5 | US-010 | Project Module 1 Discussion (File Upload and Language Preprocessing) | MUST HAVE | Web Speech API | Aditya Chikte | 3- Completed
S5 | S5 | US-011 | Document Upload Feature: Implementing PDF and DOCX Upload Functionality | MUST HAVE | React.js, File Handling Libraries | Aditya Chikte | 3- Completed
S6 | S6 | US-012 | Backend Logic: Text Extraction from Uploaded Documents | MUST HAVE | PyPDF2, python-docx | Aditya Chikte | 3- Completed
S6 | S6 | US-013 | Project Module 2 Discussion (Workflow Automation and Optimization) | SHOULD HAVE | VS Code | Aditya Chikte | 3- Completed
S7 | S7 | US-014 | Integration of Backend and Frontend | MUST HAVE | Axios, Flask, React | Aditya Chikte | 3- Completed
S7 | S7 | US-015 | Chat Interface: Designing and Integrating Conversational UI | MUST HAVE | Gradio, Tailwind CSS, Framer Motion | Aditya Chikte | 3- Completed
S7 | S7 | US-016 | Adding Authentication: Login and Logout Features | SHOULD HAVE | Firebase, NextAuth | Aditya Chikte | 3- Completed
S8 | S8 | US-017 | Testing and Debugging: Ensuring Functionality of File Upload and Chat Features | MUST HAVE | Testing Tools | Aditya Chikte | 3- Completed
S8 | S8 | US-018 | Deployment on Render: Hosting Backend | MUST HAVE | Render Hosting Platform | Aditya Chikte | 2- In Progress
S8 | S8 | US-019 | Deployment on Vercel: Hosting Frontend | MUST HAVE | Vercel Hosting Platform | Aditya Chikte | 2- In Progress
S8 | S8 | US-020 | Final Demo and Documentation | MUST HAVE | Project Files, GitHub | Aditya Chikte | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 60 | 15 | 14 | 7 | 6 | 6 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Initial project setup (repository creation, environment setup, dependencies installation) | 2024-12-04 | 2024-12-05 | Aditya Chikte | Build | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-02 | Designing database schema for document uploads and user management | 2024-12-06 | 2024-12-07 | Aditya Chikte | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-03 | Building Flask API for backend functionality | 2024-12-08 | 2024-12-10 | Aditya Chikte | Coding | 3- Completed | 8 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-04 | Integrating Gradio for conversational interface | 2024-12-11 | 2024-12-13 | Aditya Chikte | Integration Test | 3- Completed | 10 | 3 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-05 | Developing frontend with Next.js and Tailwind CSS | 2024-12-14 | 2024-12-18 | Aditya Chikte | Coding | 3- Completed | 12 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-06 | Implementing user authentication (login/logout) | 2024-12-19 | 2024-12-20 | Aditya Chikte | Build | 3- Completed | 6 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-07 | Testing document upload functionality (PDF/DOCX) | 2024-12-21 | 2024-12-22 | Aditya Chikte | System Test | 3- Completed | 6 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-08 | Debugging and refining chat functionality | 2024-12-23 | 2024-12-25 | Aditya Chikte | System Test | 2- In Progress | 7 | 0 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-09 | Deploying the application (frontend and backend integration) | 2024-12-26 | 2024-12-27 | Aditya Chikte | Others | 2- In Progress | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-10 | Final testing and submission of project | 2024-12-28 | 2024-12-29 | Aditya Chikte | System Test | 2- In Progress | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand-up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on certain AI concepts or technologies | Reviewed Infosys SpringBoard mentor sessions and referred to online resources.
Sprint 1 | Day 4 | Difficulty understanding Flask API functionality | Practiced with sample projects and clarified with mentor.
Sprint 2 | Day 5 | Challenges integrating Gradio and Flask backend | Debugged step-by-step with mentor guidance.
Sprint 2 | Day 6 | Tailwind CSS animations taking longer to implement | Watched online tutorials and applied solutions incrementally.
Sprint 2 | Day 10 | Document processing edge cases (e.g., corrupted files) | Researched handling file parsing errors and implemented fallback mechanisms.
Sprint 3 | Day 12 | Difficulty in debugging Python practice code | Watched online tutorials and applied solutions incrementally.

## Retrospection
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Started Doing | Stopped Doing | Continued Doing | Actions taken
1 | Sprint 1 | 2024-12-04 | 2024-12-08 | Aditya Chikte | Exploring transformer architecture concepts | Assuming LLMs are black boxes without understanding core logic | Participating actively in team discussions with Mentor. | Created a detailed mind map of transformers and reviewed it throught online sources and mentor.
2 | Sprint 2 | 2024-12-11 | 2024-12-15 | Aditya Chikte | Practicing retrieval techniques for RAG pipelines | Delaying code implementation due to perfectionism | Collaborating on preprocessing techniques | Tested chunking strategies and implemented a working vector database
3 | Sprint 3 | 2024-12-18 | 2024-12-22 | Aditya Chikte | Debugging issues in the FAISS retriever integration | Ignoring feedback from earlier test cases | Maintaining focus on modular coding | Solved retriever-related bugs and optimized similarity search
4 | Sprint 4 | 2024-12-25 | 30-12-2024 | Aditya Chikte | Designing the Gradio interface and later the Next.js, React, TailwindCSS and MongoDB based interface with Flask API creation for backend inorrder to make sure to provide user-friendly access | Overlooking UI/UX considerations | Collaborating on language model responses | Completed a responsive Gradio interface and collected user feedback